## Key
Term | Definition
Risk | An uncertain event or condition that, if it occurs, has a positive or negative effect on a project's objectives.
Risk Category | Source or area of project affected (Risk, Procurement, Schedule, Cost, Technical, Project etc.).
Probability | Likelihood that risk or opportunity will occur (0.1 - 1.0) expressed as a percentage.
Impact | Impact of risk on the project if risk occurs (1 - 10).
Risk Score | Probability multiplied by Impact (P*I).
Risk Response | Action which is to be taken if risk occurs.
Trigger | Indicator that risk is about to occur or has already occurred.
Risk Owner | Individual/group that the project manager assigns to watch for triggers and manage risk response if risk occurs.
Probability | Likelihood
1-20% | Very low
21-40% | Low
41-60% | Medium
61-80% | High
81-100% | Very high
Impact | Impact and Response
1-3 | Minor - Bi-weekly to monthly follow up with Risk Owner
4-7 | Moderate - Weekly to bi-weekly follow up with Risk Owner
8-9 | Significant - Weekly follow up with Risk Owner
10 | Critical - Daily follow up with Risk Owner
Risk Status | Description
Known | The existence of the risk is known to the project team. “Known” is the default status of a risk when it is initially identified.
Analysis | Risk is currently being researched to identify a possible response.
Analyzed | An analysis (or more) has been done to understand the nature of the risk (characteristics, causes, effects).
Response Known | A minimum of one response exists for the risk.
Response Selected | A response (or more) has been selected to cope with the risk, however it has not been implemented.
Response Implemented | All responses have been put into practice and the risk has been Mitigated as much as possible.
Issue | The risk has occurred.
Closed | The risk hasn’t occurred, can't occur, or has occurred and been dealt with.

## Risk Register
SWIFT Support and Enhancements Project Risk Register
Risk |  |  |  | Risk Response |  |  |  |  | Risk Status |  |  | Qualitative Ranking
No. | Date Identified | Risk Category | Risk | Response | Trigger | Mitigation | Responsible | Accountable | Date Updated | Status | Comments | Probability (%) | Impact (0-10) | Risk Score
1 | 2020-06-29 | Technical | If, when IE11 is decommissioned, the Government mandates a browser that is incompatible with some or all of SWIFT functionality AND does not leave enough time for SSI to test the new browser and make any necessary changes to SWIFT, some or all of SWIFT functionality may be impacted including the ability for Government Executives to digitally sign documents. | SSI will notify ACF CO, COR, and Business Owner. | The Government mandates a new browser that is incompatible with some or all of SWIFT functionality AND has not left enough time for SSI to test the new browser and make any necessary changes to SWIFT. | SSI identified this risk to the ACF and ASPR CORs as well as to NGITSNow (OS) on 6/29/20. SSI identified Microsoft Edge as the preferred browser. SSI will continue to test SWIFT with MS Edge to identify any required changes to SWIFT. SSI will meet with Yolanda Reid (OCIO POC for IE11 Decomm) on 3/29/21 to discuss the impacts of the browser change. | ACF/SSI |  | 2021-03-23 | Open |  | 70% | 10 | 7
2 | 2021-03-23 | Project | If the Stage Gates required for this project are not defined early in the project, SSI may not have time to develop and deliver all deliverables. | SSI will notify ACF CO, COR, and Business Owner. | The Government defines the required Stage Gates late in project not leaving SSI enough time to develop and deliver all deliverables. | SSI will identify this risk at each Monthly Status meeting. | ACF/SSI |  | 2021-03-23 | Open |  | 20% | 10 | 2
3 | 2020-06-24 | Project | If an ACF Production SharePoint instance is not available early in the project, SSI may not be able to deliver the Enterprise Collaboration feature by Sept. 2021. | SSI will notify ACF CO, COR, and Business Owner. | An ACF Production SharePoint instance is not available in time for SSI to deliver the Enterprise Collaboration feature by Sept. 2021. | SSI will identify this risk to the ACF CFT early in the project. (SSI identified this risk to the SP IPT on 3/2/20 and to the CFT on 3/12/20.) SSI will attend the Weekly ACF SharePoint IPT meetings to monitor the progress of the SharePoint 2016 Production environment. SSI will set up a weekly IPT meetings to monitor progress on the project and to discuss any issues holding up the project. Consolidation of stage gates may need to be revisited to expedite the schedule. | ACF |  | 2021-03-23 | Open |  | 10% | 8 | 0.8
2 | 2020-04-14 | Project | If the ACF SharePoint 2016 Go Live date is later than 9/28/20, SSI will not be able to deliver the Enterprise Collaboration feature before the end of the contractual period of performance (9/29/21). | SSI will notify ACF CO, COR, and Business Owner. | The ACF SharePoint 2016 Go Live date is identified as later than 9/28/21. | SSI will identify this risk to the ACF CFT early in the project. SSI will attend the Weekly ACF SharePoint IPT meetings to monitor the progress of the SharePoint 2016 Production environment. SSI will set up a weekly IPT meetings to monitor progress on the project and to discuss any issues holding up the project. Consolidation of stage gates may need to be revisited to expedite the schedule. | ACF |  | 2021-03-23 | Open |  | 10% | 5 | 0.5
Note on M3: "%username%": 1.Probability – A risk is an event that "may" occur. The probability of it occurring can range anywhere from just above 0 percent to just below 100 percent. (Note: It can't be exactly 100 percent, because then it would be a certainty, not a risk. And it can't be exactly 0 percent, or it wouldn't be a risk.)
Note on N3: "%username%": 2.Impact – We are looking at the impact that this risk will have on delivering the project ontime should it occur. The size of the impact varies in terms cost and impact on health, human life, or some other critical factor.